## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
A Gender Impact Assessment on a Skills Maintenance Course for Licensed Electrical Workers | Program | The CPD skills maintenance program provides training for electrical licence holders in Victoria. The skills maintenance program includes set training courses and resources which were examined by the GIA, and the delivery of same. Supporting policies were also subject to the GIA. | New | Yes | Tips and suggestions for inclusive facilitation practice, including language, were developed, made available to trainers, and included in trainer training. Closed captioning was added to videos. Policy that addressed reasons for granting extensions of time to complete the training was extended to include a wider range of reasons, including gender affirmation leave. Any new resources developed as part of the bi-annual update are checked to ensure a range of gender represention. | Yes | Energy Safe conducted research to ensure that the GIA considered intersectionality. In designing the the program and delivery plan, the needs of Licensed Electrical Workers with physical disability and/or accessibility requirements, gender-diverse and diverse cultural groups were considered, to ensure they felt fully included. The Instructor guides include suggestions and tips for inclusive facilitation practice and language based on gender, cultural and linguistic diversity as well as disability and accessibility. The program is delivered by RTOs who are required to provide facilities compliant with the Australian Government Disability Standards for Education 2005, which incorporate student amenities including disabled toilets and wheelchair access.
A Gender Impact Assessment on a Skills Maintenance Course for Licensed Electrical Workers | Program | The CPD skills development program provides training for electrical licence holders in Victoria. The program includes requiring licence holders to select and complete training programs of their choice, within boundaries set by the program. Supporting policies were also subject to the GIA. | New | Yes | Accessibility for regional and interstate licence holders was identified as an issue, and the boundaries defining acceptable courses were altered to ensure easier access to training for regional and interstate workers.
Energy Safe's new website design | Service | Energy Safe has undergone transformation, involving change in platform from WordPress to the Vic Govt's Single Digital (SDP) Platform. Energy Safe’s purpose - to keep Victorians energy safe and ensure energy is used confidently – guides the new website design. The website will provide an opportunity to support the delivery of one of Energy Safe’s four strategic brand pillars with a focus on an improved customer experience, including easier engagement approaches | New | Yes | All website content uplift has included inclusivity and accessibility edits. For example, a scenario to explain apprentice content was changed from male-centric to gender neutral. All videos on the website now have transcriptions. Planning for content uplift of our Community Safety section follows suggestions from the GIA. Energy Safe's content developers have attended additional workshops on inclusivity and accessibility in government communications. The website content has been developed consistent with the website content accessibility guidelines, and is generally compliant with the WCAG 2.1 standards. Energy Safe has applied the principles from Vic Gov's inclusive language guide to provide advice for web aligned projects such as removing honorifics from forms accessed on the Customer Engagement Platform. | Yes | The electrical and gas energy sector has historically had a strong representation of men and an under-representation of women. Energy Safe data based on apprenticeship contract completions in Victoria shows that less than two percent of licensed electricians (as at April 2022) are women. Anecdotal evidence also indicates there are trans and gender diverse people in training to become licensed electricians and/or within the licensed electrician workforce. With tradespeople, notably licensed electricians, as key users of the Energy Safe website, this data suggests that men are likely to comprise the largest customer (user) group from a gender lens. Insights gathering for The Ellis Jones Review (November, 2020) included a customer survey hosted on Energy Safe's website, interviews and workshops with key stakeholders and observational research. This activity included user testing with people from culturally and linguistically diverse (CALD) backgrounds and people with disability. User experience insights show that there are varying customer needs based on people’s diverse backgrounds and identities. The review included accessibility testing on ESV’s current website with various community members from CALD backgrounds (6 participants) and with people with varying accessibility requirements based on visual impairment and cognitive impairment (3 participants). Findings highlighted opportunities to improve the experiences of these community members through website design approaches such as improved use of language, design, navigation, visual cues; the review recommended addressing these accessibility issues through compliance with the Website Content Accessibility Guidelines 2.1 ( apply to the WCAG 2.1 standards)
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
1.1.1 Communicate the GEAP internally and externally (including website) with clear messaging about why gender equality, diversity and inclusion are important to ESV. | Complete | This strategy was implemented in May 2022. It was communicated internally via the intranet and cascaded down via leaders. It was also published on the external website. | In 2023 People Matter Survey: - 86% of respondents agreed with the statement My organisation uses inclusive and respectful images and language (an increase of 5% on 2021 result) - 89% of responents agreed with the statement I feel culturally safe at work (an increase of 9% on 2021 result) | 2022 | CEO, HR | X |  | X | X | X | X | X
1.1.2 Continue with awareness raising events to celebrate key dates on the diversity calendar (such as International Women’s Day, International Day of People with Disabilities, NAIDOC Week, Harmony Day, Wear it Purple Day, Pride Week, Equal Pay Day) | Ongoing | Acknowledge This! workshop, recgonised RUOK, World AIDS Day 2023, World Diabetes Day, Women's Health Week and are participating in the Midsumma Pride March. In 2022-2023 we held celebrations for International Women's Day, Multicultural week, IDAHOBIT, Wear it Purple, International Pronoun Day, World Mental Health Day and International Day of People with Disability. We also participated in R U OK day. In addition we offered an indigenous walk and an Acknowledge this Workshop. In 2021-22 we celebrated R U OK day, International Week of Deaf people, International Day of people with disability, IDAHOBIT, NAIDOC week and Cultural Diversity week. We also acknowledged Reconciliation Week. | We have had high participation in celebration of days of significance on the diversity calendar. | Ongoing | D&I Council | X |  | X | X | X | X | X
1.2.1 Establish terms of reference, including roles and responsibilities for the Council and sponsorship members | Complete | The first Diversity and Inclusion Council (D&I) Council meeting was held in October 2022 and the terms of reference, including roles and responsibilities were established in October 2022. The CEO is chair of the Council that includes management and staff representatives. | D&I council established with clear terms of reference. The Council continues to operate. | 2022 | D&I Council, HR | X |  | X | X | X | X | X
1.2.2 Develop D&I Dashboard that is reviewed quarterly by the Council, ELT and ESV Commission. This will include gender and diversity data and progress of the GEAP actions | Complete | The Dashboard was created in 2022 and first presented at the D&I Council meeting in February 2023. The Dashboard has been presented and reviewed by the Council on a quarterly basis along with progress against GEAP actions | D&I dashboard in place that is reviewed quarterly. | 2022 | D&I Council, HR | X |  | X | X | X | X | X
1.3.1 Leaders take practical actions to challenge traditional notions of gender role types to support the achievement of increases in proportional representation (such as job rotations, secondments, communication of employees undertaking counter- stereotypical roles) | Ongoing | Opportunities are taken when possible. For example, job rotation in Line Clearance Advisor role to encourage proportional representation. We have also publicised men taking parental leave and/or adopting flexible working arrangements to promote uptake. |  | 2022 | All Leaders | X |  | X | X | X | X | X
1.3.2 Diversity and inclusion indicators/measures are included in the performance plans of all ELT members and over time cascaded to all leaders | Not started | Not due for completion until 2024 |  | 2024 | All Leaders | X |  | X | X | X | X | X
1.4.1 Enhance exit interview processes to gain insights into employee experiences and use insights to refine inclusive practices | Complete | Exit interview process has been amended to gain additional data on gender and further insights on employee experiences. | Energy Safe has gained some useful insights, however, given the low turnover and some respondents choosing not to disclose their gender, the sample size is currently too small to identify meaningful trends. | 2022 | HR | X |  | X | X | X | X | X
1.4.2 Conduct pay equity analysis on an annual basis and provide reporting to the ELT | Ongoing | The Executive Leadership Team have been provided with reporting on the following metrics on an annual basis • Workforce composition by Gender/Job Grade • Gender Distribution by Employment Basis • New Starters by Gender/Job Grade • Promotions by Gender/Job Grade • Progression increases by Gender • Exits by Gender/Job Grade • Gender Segregation within the workforce | Reporting provided, key trends identified. Current reporting systems do not enable efficient and accurate reporting so manual preparation of reports compiled. A new HR information system planned for implementation during 2024/2025 should deliver improved reporting capabilities. | 2022 & Ongoing | HR | X |  | X | X | X | X | X
1.4.3 Review pay practices that can lead to gender-based inequities such as gender pay differences for commencement salaries and progression outcome by gender | Ongoing | The progression outcomes are presented by gender as part of the Summary paper. | In Financial year 2022/2023, 13 women received progression vs 21 men, which is a high proportion when taking into account the workforce composition. In the audit of 2021, 16 women and 14 men received a progression increase | Annually | HR | X |  | X | X | X | X | X
1.4.4 Enhance our systems to enable capture and reporting of intersectional data (ie data on age, Aboriginality, disability, cultural identity, religion and sexual orientation) and data on employee who identify as gender diverse | Not started | Energy Safe is due to implement a new HR Information System in 2024/2025 which will enable enhanced ability to capture intersectional data. The HR team has commenced collecting some of these data manually. | This was due originally due to be implemented by 2023, but due to digital transformation during the year, and other priorities, it has been rescheduled. | 2023 | HR | X |  | X | X | X | X | X
2.1.1 Deliver inclusive leadership education to all leaders to build the capability to lead inclusively, promote gender equality, diversity and psychological safety, as well as an understanding of intersectional gender equality. Leaders to cascade learnings to their team members | Complete | Energy Safe engaged Diversity Partners to conduct four inclusive leadership & Unconscious Bias workshops for leaders in July and September 2022. | We had a high participation rate and received a lot of positive feedback from participants. | 2022 | HR, All leaders | X |  | X | X | X | X | X
2.1.2 Integrate inclusive leadership capability into the competency framework and development curriculum | In progress | The capability framework was developed during 2023, including leadership elements. It will be further reviewed during 2024/25 to align with the progression framework that supports the Enterprise Agreement. Bargaining on the Agreement is due to commence during 2024. |  | 2023 | HR | X |  | X | X | X | X | X
2.1.3 Educate staff on LGBTIQ+ inclusion, disability confidence and cultural awareness. Provide | Complete | Energy Safe has utilised numerous forums to educate staff on LGBTIQ+ inclusion, disability confidence and cultural awareness. This included a celebration of IDAHOBIT, education about use of pronouns and incorporating pro-nouns into e-mail signatures. Energy Safe has implemented a number of cultural awareness initiatives including an Aboriginal cultural walk to educate staff about indigenous heritage and Acknowledgement of country workshops to develop a deeper understanding of it's relevance and meaning | There has been a strong uptake of pro-nouns into e-mail signatures, feedback and participation in indigenous awareness workshops has been very positive. Acknowledgement of country has been embedded into Energy Safe meetings and other relevant forums. | 2024 | HR, All leaders | X |  | X | X | X | X | X
2.1.4 Integrate inclusive leadership principles into ESV’s Leadership Development programs. | Not started | See 2.1.2 |  | 2022 | HR | X |  | X | X | X | X | X
2.2.1 Provide regular compulsory learning opportunities to reinforce behavioural standards for all employees to assist with the prevention of bullying, harassment, discrimination and victimisation | Ongoing | Energy Safe is progressively updating relevant Policies and consults and communicates with employees as new and updated Policies are issued. Key Policies and relevant training are delivered through online training modules. | People Matter Survey results: People in my workgroup treat each other with respect 87% in 2023, which is -1% from 2021. In 2023, 10% reported that they are experiencing bullying, which is -2% from 2021. In 2023, 71% agree that Organisation takes steps to eliminate bullying, harassment and discrimination (-3% on 2021 figure). In 2023, 91% agree that organisation encourages respectful workplace behaviours, which is a 5% increase on 2021 results. | 2022 | HR | X |  | X | X | X | X | X
2.2.2 Review and enhance the complaints process to ensure it provides timely, trusted and accessible processes. Communicate the updated process | In progress | An external legal review of the complaints policy has been undertaken with improvements made to the Staff Internal Complaints/Grievance form to improve clairty and usability. The organisational consultation and implementation of the updated Complaints Policy and some other key associated HR policies are on hold pending the successful negotiation of Energy Safe's Enterprise Agreement which nominally expires on 30 June 2024. |  | 2022 | HR | X |  | X | X | X | X | X
3.1.1 Review and refresh ESV’s Recruitment, Selection and Appointment Policy and processes in line with best practice inclusion and diversity recommendations (provided by an external specialist). This includes:review and broaden strategic recruitment partnerships to attract women and gender diverse people | In progress | The Recruitment, Selection and Appointment policy was reviewed and updated in May 2023 to expand on D&I requirements. This included a requirement to brief agencies on gender equality and diversity commitments and expectations. This is followed during recruitment processes. | Further training on Unconscious Bias is to be rolled out in 2024. People Matter Survey results : In 2023, 57% believe that recruitment processes in my organisation are fair. (not asked in 2021), 35% believe promotion processes are fair (not asked in 2021) | 2023 | HR |  |  | X | X | X | X
HR
HR
Brief external recruitment agencies on gender equality, and diversity commitments and expectations | Complete | The Recruitment, Selection and Appointment policy was reviewed and updated in May 2023 to expand on D&I requirements. This included a requirement to brief agencies on gender equality and diversity commitments and expectations. | Policy implement and practices adopted | 2022-2023 | HR |  |  | X | X | X | X
monitor and measure data on applications received for male- dominated roles, short- listed candidates and offers accepted by gender | Ongoing | Data has been collated on an annual basis. | Further improvements required to improve reporting capability to capture all applicant types as at present we can only capture data from applicants who apply via SEEK. The implementation of a new recruitment system with improved reporting functionality needs is required to address this issue further. | 2022-2023 | HR |  |  | X | X | X | X
encourage women and diverse representation on candidate long and short-lists and interview panels | Complete | A review of our Family and Domestic Violence policy was undertaken in February 2023 and it was updated to include changes to Family and Dovmestic Violence Leave provisionis for casual employees. This was recommunicated to all Energy Safe's people via the intranet. |  | 2022-2023 | HR |  |  | X | X | X | X
hiring managers to complete recruitment and selection training including an understanding on the potential impact of unconscious bias. | Complete | Leaders completed training on Unconscious Bias in 2022. | High attendance at training sessions | 2022-2023 | HR |  |  | X | X | X | X
3.1.2 Integrate gender equality and diversity into talent management, promotion and succession planning processes | In progress | A gender equality and diversity lense has been applied for talent management and succession planning annual processes for the Executive Leadership and Senior Leadership Teams. Women have been identified and placed on tailored development plans. | A woman was seconded from the position of Head of Gas and Pipeline Infrastructure Safety to the Executive position of General Manager, Gas & Pipeline Safety & Technical Regulation which is typically a male dominated role. We also had two female Senior Leaders acting in Executive positions to cover annual leave including Head of People Services covering for Chief Operating Officer and Head of Regulatory Policy and Legislation relieving the General Counsel and General Manager - Legal, Governance and Regulatory Policy. | 2024 | HR |  |  | X | X | X | X
3.1.3 Update the Parental Leave policy and supporting tools to reflect the Enterprise Agreement provisions | Complete | Policy and supporting tools have been updated to reflect the Enterprise Agreement provisions. | Policy implemented | 2022 | HR |  |  | X | X | X | X
3.1.4 Review our Family and Domestic Violence leave provisions in relation to best practice and recommunicate to all our people | Complete | A review of our Family and Domestic Violence policy was undertaken in February 2023 and it was updated to include changes to Family and Dovmestic Violence Leave provisionis for casual employees. This was recommunicated to all Energy Safe's people via the intranet as well as being cascaded down through line managers. | In 2023 PMS survey, 86% agreed with statement My organisation would support me if I needed to take family violence leave, this is a 6% increase on 2021 result. | 2022 | HR |  |  | X | X | X | X
3.2.1. Ensure all leaders and employees are aware of, and promote, the use of flexible arrangements across technical and non-technical roles, to support the full participation in employment at ESV and balancing personal and professional lives | Complete | Leaders have been kept informed of flexible arrangements available and HR provides regular guidance to managers to assist them to have relevant discussions to negotiate flexible arrangements. A Hybrid Working Policy was implemented in May 2023 to embed hybrid work practices that assist employees to balance their work and personal lives | In 2023 PMS survey, 89% of respondents agreed with statement My manager supports working flexibly. | 2022 & Ongoing | HR, All leaders |  |  | X | X | X | X
3.2.2 Promote storytelling about the lives and experiences across all employee groups; for example, profile men and employees with diverse backgrounds who have caring responsibilities or community-based commitments and promote part-time opportunities to all genders. Use a variety of communication approaches to promote visibility and benefits | Complete | Energy Safe has promoted the uptake of flexible working arrangements among men in the organisation by showcasing individual stories to further promote visibility and benefits | In 2023 PMS survey, 89% of respondents agreed with statement My manager supports working flexibly. | 2022 & Ongoing | HR, Strategic Comms |  |  | X | X | X | X
4.1.1 Set gender targets for external recruitment shortlists – for example, at least one woman on the recruitment shortlist for all leadership levels. | In progress | Gender targets have not yet been implemented following an external legal review of Recruitment and Selection Policy and advice received stating that Energy Safe will need to establish how the proposed measure will remedy inequality. The advice indicated Energy Safe will need to conduct an assessment and compile substantial evidence to demonstrate that the recruitment requirements qualify as a "special measure". |  | 2022 | ELT | X |  | X |  | X |  | X
4.1.2 Establish a mentoring program for high potential women | In progress | During 2023 Energy Safe implemented a new Operating Model that has involved establishing new systems, new processes and new organisational structures. These changes have placed resourcing and time constraints on establishing formal mentoring programs. | Some high potential senior women leaders have been working with coaches during 2023. | 2023 | HR | X |  | X |  | X |  | X
4.1.3 Prioritise gender balanced graduate placements and internships to attract engineering and other STEM based students. This may include joint initiatives with partners to promote gender diversity in apprenticeships | Not started | During 2023 Energy Safe implemented a new Operating Model that has involved establishing new systems, new processes and new organisational structures. These changes have placed resourcing and time constraints on. prioritising graduate placements and internships. There have been no graduate placements or internships, or capacity to engage with partners during this time. | Energy Safe will be undertaking additional recruitment during 2024, including for engineering skills and will seek to recruit relevant skills and gender balance. | 2022 & Ongoing | HR | X |  | X |  | X |  | X
4.1.4 Leaders commit to a Panel Pledge - whenever they are asked to speak or are invited to be involved in or sponsor a panel or conference (both internal and external) they ask the organiser about the efforts to ensure women (and broader aspects of diversity) are represented and highlight their commitment to diversity. | In progress | The Executive endorsed commitment to the Panel Pledge, and discussed this with senior management recognising the value of involving women (and broader aspects of diversity) during 2023. |  | 2023 | All Leaders | X |  | X |  | X |  | X
4.2.1 Complete a review of ESV’s public presence (website and social media channels) to ensure diversity and inclusion is integrated into the new organisation’s values and Employee Value Proposition (EVP) | In progress | Not due for completion until 2024 | Progress has been made as part of the GIA on the new website | 2023-2024 | HR, Strategic Comms | X |  | X |  | X |  | X
4.2.2 Develop a transition to retirement program that optimises knowledge transfer | Complete | Energy Safe incorporated a transition to retirement clause in the ESV Enterprise Agreement 2020. This clause allows employees to provide extended notice of retirement which enables them to receive training in mentoring skills and actively participate in a skills and knowledge transfer process so that there can be a seamless handover to a replacement Employee by the date of the Employee's retirement | So far 3 employees have successfully participated in Energy Safe's Transition to Retirement program. | 2022 | HR | X |  | X |  | X |  | X
Select one | Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
There are currently two people responsible for leading implementation of the strategies and measures in the GEAP, and both are within the Customer and People Experience Division of Energy Safe. Implementation of some strategies and measures has been delayed reflecting the reallocation of resource time to support a significant transformation program that has been undertaken in the organisation the requirements of which were not known at the time of developing the GEAP. Energy Safe will be establishing an Capability and Organisational development team during 2024 that will provide additional resources to assist implementing the GEAP.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | No | As of 30 June 2021, our workforce comprised of 206 employees with an overall gender composition of 41% women and 59% men. As of 30 June 2023, our workforce comprised 224 employees with an overall gender composition of 39% women and 61% men. The representation of women at the Executive Leadership Team as of 30 June 2023 is 60 %, this is an increase of 17% since the June 2021 audit. Whilst, there is high representation of women at the Executive level, women are still more highly represented than men at the lower classifications. No progress has been made against this indicator. | Yes | No | No | Yes | Yes | Yes | Yes
Gender composition of governing bodies | No | The gender composition of the governing body has remained stable. All 3 Commission roles and the CEO role are held by women. | Yes | No | No | Yes | Yes | Yes | Yes
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | Our 2021 audit, had an overall median annualised base salary pay gap of 29.6%. As of June 2023, the median annualised pay gap is 22.2%. At the ELT level, the pay gap decreased from 6.1% to 1.9%. At the ESV 4 level there has also been a reduction from 4.9% to 0%. We consider this to demonstrate measurable progress against this indicator. | Yes | No | No | Yes | Yes | Yes | Yes
Sexual harassment in the workplace | Yes | Our 2021 data showed that there had been no formal sexual harassment complaints. Our 2021 People Matter Survey results showed that 4% of employees who responded to the survey had experienced sexual harassment in the workplace. Our 2023 data showed that there had been no formal sexual harassment complaints. Our People Matter survey results showed that 3% of employees who had responded to the survey reported they had experienced sexual harassment in the workplace. We note that whilst there is nil reporting of sexual harassment, it is important to continue to communicate and raise awareness about sexual harassment in the workplace. The sexual harassment policy is currently being revised and education sessions are scheduled for 2024. There has been some slight progress against this indicator. | Yes | No | No | Yes | Yes | Yes | Yes
Recruitment and promotion practices in the workplace | No | In the 2021 audit, women represented 68% of our new recruits. In 2023, women represented 47% of the new recruits. Promotions In our 2021 audit 2 women and 1 man was promoted. In the financial year ending 2023, we had an equal number of women and men promoted (2 women and 2 men). There has been no progress against this indicator. | Yes | No | No | Yes | Yes | Yes | Yes
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | As of 30 June 2021, 42% of employees had formal flexible working arrangements in place and 25% of these employees were women while 75% comprised of men. The majority of employees with formal flexible working arrangements are at the ESV 2 to ESV 4 grade, with the highest proportion at ESV 4 level. There are a number of employees who access flexible working arrangements on an informal basis. This data does not take into account any informal flexible arrangements. There were zero employees accessing employee leave. As of 30 June 2023, 55% of employees had formal flexible working arrangements in place and 33% of these employees were women. The majority of employees with formal flexible working arrangements continue to be at the ESV 2 to ESV 4 level. There are a substantial amount of employees who access flexible working arrangements on an informal basis and all employees are working within a hybrid model which requires them to attend the office for 2 days per week (and pro rata for part time staff). There has been a positive trend in uptake of formal flexible working arrangements, and further progress can be made in regard to women and their uptake of formal flexible working arrangements. In 2023, 69 employees accessed carers leave. Overall progress has been made against this indicator. | Yes | No | No | Yes | Yes | Yes | Yes
Gendered segregation within the workplace | Yes | In 2021, the gendered segregation data indicated that Technicians and Trade Workers were significantly over represented by men and Clerical and Administrative Workers were over represented by women. There was also a higher proportion of men in both Professional and Managerial roles. This continues to be the case, but improvements have been made within these categories.In 2021, women represented 37% of the Managerial classification and in 2023 this increased to 43%. In 2021, women represented 92% of the Clerical and Administration Workers classification, but this dropped to 81% in the 2023 audit. In addition, there was a positive shift in the Technicians and Trade Workers category as the percentage of women in this category increased from 4% to 10%. | Yes | No | No | Yes | Yes | Yes | Yes
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled